## 시트1
Milestone 1 - Git Commit Work Division
Development Area | Eunjoo Jung | Errin James | Shared
Project Setup | Backend/server setup, DB configuration | Frontend/client setup | Repository structure and integration decisions
Authentication | User model, registration API, login API, auth middleware | Registration page, login page, logout controls, frontend errors | End-to-end authentication verification
Course Management | Course model, CRUD API, ownership validation | Course list, create/edit/delete UI | Integration and bug fixing
Task Management | Task model, CRUD API, validation, course association | Task form, edit/delete UI, task fields | Integration and workflow verification
Progress / Status | Backend progress/status logic | Progress/status controls and display | End-to-end verification
Dashboard | Dashboard API/query/data handling | Dashboard layout, task display, responsive UI | Integration and final behavior checks
Database | PostgreSQL schema, migrations, relationships | Review and frontend data requirements | Schema review
API Contract | Define/update REST endpoints | Verify frontend requirements | Agree on request/response structure
Backend Testing | API/auth/database tests | Review when needed | Integration test planning
Frontend Testing | Support if API mocks/data needed | UI/component/interaction tests | End-to-end test cases
Bug Fixes | Backend/data/API fixes | Frontend/UI fixes | Integration bugs
Documentation | Backend/database/API documentation | Frontend/UI documentation | README, milestone report, final setup instructions
Screenshots / Evidence | Backend/API evidence where needed | UI screenshots | Final report evidence
Pull Request Review | Review Errin's PRs | Review Eunjoo's PRs | Major integration decisions
Final Integration | Backend fixes and verification | Frontend fixes and verification | Final runnable MVP
Milestone Tag / Final Check | Participate | Participate | Confirm final commit and milestone-1 tag
Note: “Shared” does not mean that both team members create the same commit together. It means that both members participate in reviewing, verifying, discussing, or making decisions about that task. The actual Git commit should be made by the team member who performed the corresponding work, using their own GitHub account.
Based on the Milestone 0 feedback, both team members should make multiple small, meaningful commits during each milestone rather than committing all work at once. This will help demonstrate balanced contribution and follow standard industry Git practices.